## Reserve fund
HIGH POINT SOUTH
RESERVE FUND UPDATE - 2014
DESCRIPTION OF ITEM | YEAR | 2014 AMOUNT | DESCRIPTION OF TASK
Roof replacement | 2027 | 220000
Storage units | 2020 | 62000
Walkway/deck repair | 2021 | 20000 | work need to be accomplished in 2014 - needs to be done every 7 years, changed year from 2018
Wood railings (wind guard) | 2015 | 450000 | from EFIS installation observation, moved up from 2021 to 2015
Exterior building | 2053 | 1008025 | from EFIS program, added 300-K to recent amount for increase and engineering - assumes 40 yr life
Exterior bldg. facing resealing (V joints) | 2015 | 50000 | 4 towers - one every two years (2013/2015/2017/2018) at 12,500.00
Common area doors (fire, stair well, elect.) | 2028 | 60000 | starting 2013, one floor per year - changed from 2013 to 2028 (for completion of 1 floor a year)
Exterior stucco painting (towers) | 2021 | 40000 | moved from 2015 to 2021, work just recently completed - 10 yr life
Elevators | 2025 | 400000 | moved from 2055 to 2025 - received estimate of 200,000.00 each
Trash compactor | 2024 | 21000 | new in 2013/2014 - assume 10 year life
Swimming pool shell coat | 2015 | 20000 | moved from 2013 to 2015
Swimming pool equipment | 2020 | 20000 | may need small amounts each year for repairs/replacements
Swimming pool deck | 2017 | 40000 | moved from 2020 to 2017 due to recent observations
Parking lot pavement | 2019 | 175000
Sidewalks/pads/landscaping | 2020 | 10000
Exterior lighting | 2014 | 25000 | working on lighting system now - expect savings and will need to extension of time
Alarm system | 2030 | 100000 | recently upgraded, moved from 2020 to 2030
TOTAL |  | 2721025